## Policy 2014
F-QMS-008
Action Plan : SCG Logistics Co.,Ltd. |  |  | Year 2014 |  |  | Dept. System Development Sect. - | [16 empty] | Date:_8/8/13_______________
No. | Company / Dept. Plan | Dept./ Sect. Plan | Control Point |  |  |  | Person | Due |  |  |  |  | Plan / Actual 2014 | [11 empty] | Plan / Actual 2015 |  |  |  | Evaluation
|  |  | Control item | Current | Target | +/- | in charge | Date |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Process | Results | Student
1 | Serve SCG Growth (Multi-channel order management platform) | 1.1.1 System integration with SCG Paper: SKIC Interface TMS | Finish |  | 100% | - | Sarunya/Vatcharm | Feb-13 | Plan |  |  | 30% | 70% | 100%
[9 empty] | Actual |  |  | 30% | 50% | 50% | 60% | 65% | 70% | 90% | 100%
|  |  | ลดระยะเวลาในการจัดทำรายงานค่าขนส่ง | 1 วัน | 0 วัน |  |  |  | Plan | [10 empty] | 0 | 0 | 0
Actual
|  |  | ลดงานของ user ในการจัดทำรายงานค่าขนส่ง | 1 งาน | ไม่มีงาน |  |  |  | Plan
Actual
|  |  | ลดระยะเวลาการรับรู้ Performance | 30 วัน | 1 วัน |  |  |  | Plan | [10 empty] | 1 | 1 | 1
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Dec-12 | Plan |  |  | 30%
[9 empty] | Actual |  |  | 30%
|  | - UAT | Finish |  | 70% |  |  | Jan-13 | Plan |  |  |  | 70%
[9 empty] | Actual |  |  |  | 50% | 50% | 60% | 65% | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Feb-13 | Plan |  |  |  |  | 100% |  |  |  | 90% | 100%
[8 empty] | 2013-07-01 | Actual | [8 empty] | 80% | 100%
1 | Leverage Existing Competencies and Capture New Opportunities | 1.1 SCGL e Portal: Ordering, Scheduling, Track & Trace, VMI | Finish |  | 100% | - |  |  | Plan
| (Order Management by Segmentation and Integrated IT solutions with Customers) | [7 empty] | Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 1.2 System Integration with strategic customer | Finish |  | 100% | - |  |  | Plan
|  | (Thai Container Group: pilot TCSP) | [6 empty] | Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 1.3 System Integration with strategic customer | Finish |  | 100% | - |  |  | Plan
|  | Mitrphol (transportation & billing) | [6 empty] | Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 1.4 SAP PI implementation: Replace existing interface Ceramic, TSTH, Vitamilk | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 1.5 SCTL Link Revamp | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 1.6 New Transport OK system | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
2 | Warehouse expansion for customer response and efficiency improvement | 2.1 Warehouse Management System for Complex warehouse operation: CDC Wangnoi / RDC KK/CM/SR | Finish |  | 100% | - | Thaworn | 2015-05-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 2.2 Setup ESC system at ESC5 | Finish |  | 100% |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
3 | Create growth platform for regional integration | 3.1 SAP implementation for new company registration: Cambodia, Lao, Vietnam | Finish |  | 100% | - | Sarun | 2014-06-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 3.2 TMS-C enhancement to serve OV business: Myanmar | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 3.3 TMS-C enhancement to serve JV business: Production and Truck visibility for JV in South China | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
4 | Strengthen Infrastructure to Sustain Business | 4.1 Supply Chain Visibility Enhancement (Roll-out SCV platform & Alert management system) | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 4.2 Logistics Information (Truck Supply Availability Systm) | Finish |  | 100% | - |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 4.3 Management Information System: Sales, Operation, Carrier report | Finish |  | 100% | - | Tatthep | 2014-09-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 5.Accounting Web Upgrade | Finish |  | 100% | - | Sineekarn | 2014-09-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 6. WMS for DC Rangsit | Finish |  | 100% | - | Sarun | 2014-07-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 7. WMS for Mitr Phuviang | Finish |  | 100% | - | Saranachon | 2014-02-01 | Plan | 30% | 70%
[9 empty] | Actual |  | 50% | 60% | 65% | 65% | 65% | 0%
|  |  | ควยคุมการจ่ายสินค้าแบบ FIFO | 0% | 100% |  |  |  | Plan |  | 100%
[9 empty] | Actual |  | 10% | 10% | 10% | 10% | 10% | 0%
|  |  | มีข้อมูลในระบบทั้งหมด | 0% | 100% |  |  |  | Plan |  | 100%
[9 empty] | Actual |  | 50% | 75% | 80% | 80% | 80% | 0%
|  |  | Stock Accuracy | 0% | 100% |  |  |  | Plan |  | 100%
[9 empty] | Actual |  | 95% | 95% | 95% | 95% | 95% | 0%
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan | 30%
[9 empty] | Actual | 15% | 25% | 30%
|  | - UAT | Finish |  | 70% |  |  |  | Plan |  | 70%
[9 empty] | Actual |  | 25% | 30% | 35% | 35% | 35% | 0%
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan |  | 100%
[9 empty] | Actual |  | 50% | 60% | 65% | 65% | 65% | 0% | [14 empty] | D
|  | 8. WMS for Kubota Wangnoi | Finish |  | 100% | - | Saranachon | 2014-08-01 | Plan | [10 empty] | 100%
Actual
|  |  | ควยคุมการจ่ายสินค้าแบบ FIFO | 0% | 100% |  |  |  | Plan | [10 empty] | 80% | 85% | 90% | 95% | 100%
Actual
|  |  | มีข้อมูลในระบบทั้งหมด | 0% | 100% |  |  |  | Plan | [10 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Actual
|  |  | Stock Accuracy | 0% | 100% |  |  |  | Plan | [10 empty] | 70% | 80% | 90% | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan | [10 empty] | 30%
[9 empty] | Actual | [10 empty] | 15% | 30%
|  | - UAT | Finish |  | 70% |  |  |  | Plan | [10 empty] | 70%
[9 empty] | Actual | [10 empty] | 35% | 40% | 60% | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan | [10 empty] | 100%
[9 empty] | Actual | [10 empty] | 50% | 70% | 90% | 90% | 90% | 90% | 90% | 90%
|  | 9. Data Warehouse upgrade : Pilot SAP Cambodia | Finish |  | 100% | - | Tatthep | 2014-06-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 10. Claim & Complain Enhancement (Phase2) | Finish |  | 100% | - | Nantanit | 2014-08-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 11. VMI for Affiliate Customer | Finish |  | 100% | - | Thanasien | 2015-10-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 12. GPS Pilot test in Indonesia (Ready-Mix) | Finish |  | 100% | - | Eakapon | 2014-06-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 13. IT Solution for Kubota Spare Part | Finish |  | 100% | - | Mongkolchai | 2014-12-01 | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  |  | xx | xx | xx |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan
Actual
|  | 14. WMS Kubota Lube | Finish |  | 100% | - | Saranachon | 2014-11-01 | Plan | [11 empty] | 30% | 70% | 100%
[9 empty] | Actual | [11 empty] | 30% | 50% | 90% | 100%
|  |  | ควยคุมการจ่ายสินค้าแบบ FIFO | Est. 70-80% | 100% |  |  |  | Plan | [13 empty] | 98% | 100%
[9 empty] | Actual | [13 empty] | 100% | 100%
|  |  | มีข้อมูลในระบบทั้งหมด | 50% | 100% |  |  |  | Plan | [13 empty] | 90% | 100%
[9 empty] | Actual | [13 empty] | 85% | 100%
|  |  | Stock Accuracy | 98% | 100% |  |  |  | Plan | [13 empty] | 100% | 100%
[9 empty] | Actual | [13 empty] | 90% | 100%
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan | [11 empty] | 30%
[9 empty] | Actual | [11 empty] | 30%
|  | - UAT | Finish |  | 70% |  |  |  | Plan | [12 empty] | 70%
[9 empty] | Actual | [12 empty] | 50% | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan | [12 empty] | 80% | 100%
[9 empty] | Actual | [12 empty] | 70% | 90% | 100%
Approve by _____________________ Date _______________________
F-QMS-008 (REV.3)
Plan
Actual
Plan
Actual
Note on T17: Training - completed Maintain AR/AP - In-progress
Note on J18: Revise
Note on T18: maintain 1. ค่าเก็บลูกค้า - ม้วน-> พี่จูบ maintain แล้วเสร็จ, พี่อี๊ดเอาเข้าระบบ - เศษโรงอัด ราคา Backhaul (อยุธยา, ขอนแก่น) -> พี่อี๊ด maintain เพิ่ม โดยใช้ Template เดิม 2. ค่าจ่าย ผรม. - ม้วน -> พี่ก้อง maintain แล้วเสร็จ อยู่ระหว่างตรวจสอบความถูกต้อง - เศษโรงอัด ราคา Backhaul (อยุธยา, ขอนแก่น) -> พี่อี๊ด ส่งราคาให้พี่ X
Note on R252: Remark: Terminate เนื่องจากไม่สามารถ Manage ได้ครบตามเป้า โดยมีสาเหตุหลักมาจากการที่ลูกค้าระบุเงื่อนไขในการทำระบบมาไม่ครบ ทำให้การออกแบบคลาดเคลื่อน ปัจจุบันมีการใช้ In-housed software ในการคุม stock
Note on AC264: Remark : เนื่องจากมีปัญหาขัดแย้งด้านโครงสร้างทำให้หน้าจอ Reconcile ตรวจนับ และการคิดเงินแยกไปอยู่ทที่ Access และ Excel ตามลำดับ ซึ่งแก้ไขในตอนที่ย้ายไปยัง DC Rangsit ใหม่
Note on Y363: Remark: PDCA ปรับปรุงเรื่องการจ่าย FIFO ให้สอดคล้องกับความเร็วในการทำงาน

## Control chart
บริษัทเอสซีจี โลจิสติกส์ แมเนจเม้นท์ จำกัด
กราฟควบคุมแสดงผลเปรียบเทียบกับเป้าหมาย
Action Plan No. ___IT Project Management 2013________________________________________________________
หัวข้อควบคุม/เป้าหมาย | สูตรการคำนวณ |  |  |  | ผู้รับผิดชอบ |  | หน่วยงาน |  | ช่วงควบคุมปกติ |  | หมายเลขเอกสาร |  | วันที่จัดทำเอกสาร
% Project Achievement rate | Number of project meet objective |  |  |  | SD Manager |  | System Development |  | 90% |  |  |  | 2013-08-01
Total project
เดือน | ม.ค. | ก.พ. | มี.ค. | เม.ย. | พ.ค. | มิ.ย. | ก.ค. | ส.ค. | ก.ย. | ต.ค. | พ.ย. | ธ.ค. | หน่วย :
เป้าหมายรายเดือน |  | 1 | 1 | 2 |  | 3 | 6 | 1 | 1 | 1 | 4 | 5 | รายเดือน
ผลรายเดือน |  | 1 | 1 | 1 |  | 3 | 6
เป้าหมายสะสม | 0 | 1 | 2 | 4 | 4 | 7 | 13 | 14 | 15 | 16 | 20 | 25
ผลสะสม | 0 | 1 | 2 | 3 | 3 | 6 | 12 | 12 | 12 | 12 | 12 | 12 |  | สะสม
สัดส่วนความสำเร็จสะสม | 0% | 4% | 8% | 12% | 12% | 24% | 48%
หมายเลขเอกสารวิธีการขจัดสิ่งผิดปกติ
รายเดือน
สัดส่วนความสำเร็จสะสม
ช่วงควบคุมปกติ
......................
ผล
เป้าหมาย
สะสม

## SD KPIs
1. Project achievement rate
|  |  |  | Plan / Actual 2013 | [11 empty] | Plan / Actual 2014
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Total Project
|  |  | Plan | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 1 | 0 | 1 | 3 | 1 | 0 | 0 | 0 | 10
|  |  | Plan' | 0 | 1 | 1 | 2 | 0 | 2 | 3 | 0 | 1 | 0 | 4 | 2 | 0 | 0 | 0 | 2 | 18
|  |  | Plan'' (project re-schedule) | [16 empty] | 2 | bar: Plan / Actual 2013 Jun; Plan / Actual 2013 Nov
|  |  | Total Plan | 0 | 1 | 1 | 2 | 0 | 3 | 6 | 0 | 2 | 0 | 5 | 5 | 1 | 0 | 0 | 2
|  |  | Actual | Plan / Actual 2013 Feb: 1; Plan / Actual 2013 Mar: 1; Plan / Actual 2013 Apr: 1; Plan / Actual 2013 May: 0; Plan / Actual 2013 Jun: 3; Plan / Actual 2013 Jul: 6 | 12
|  |  | Accumulate Plan | 0 | 1 | 2 | 4 | 4 | 7 | 13 | 13 | 15 | 15 | 20 | 25
|  |  | Accumulate Actual | Plan / Actual 2013 Jan: 0; Plan / Actual 2013 Feb: 1; Plan / Actual 2013 Mar: 2; Plan / Actual 2013 Apr: 3; Plan / Actual 2013 May: 3; Plan / Actual 2013 Jun: 6; Plan / Actual 2013 Jul: 12
|  |  | % Monthly Achievement | #DIV/0! | 100% | 100% | 50% | #DIV/0! | 100% | 100% | #DIV/0! | 0% | #DIV/0! | 0% | 0%
|  |  | % Plan Achievement | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
|  |  | % Accumulate Achievement | Plan / Actual 2013 Feb: 100%; Plan / Actual 2013 Mar: 100%; Plan / Actual 2013 Apr: 75%; Plan / Actual 2013 May: 75%; Plan / Actual 2013 Jun: 85.71%; Plan / Actual 2013 Jul: 92.31%
Business Plan 2013 | Type | IT Plan 2013 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | PIC | IT Plan | Type | Status | Investment
1. Build up capacity and Improve service level for SCG | AP | 1.1.1 | System integration with SCG Paper: SKIC Interface TMS | 92.31% Jul: 100% |  | Sarunya/Vatcharm | System integration with SCG Paper: SKIC Interface TMS | Productivity | WIP
| AP | 1.1.2 | System integration with SCG Paper: Interface TCG System to TMS | 92.31% Jan: 100% |  | Sarunya
2. Warehouse expansion for customer response and efficiency improvement | AP | 2.1 | Setup WMS and IT infrastructure at RDC Khonkaen | 92.31% Jul: 100% |  | Nattawut / Thaworn | Setup WMS and IT infrastructure at RDC Khonkaen | Productivity | Completed
| AP | 2.2 | Setup ESC system at ESC4 | 92.31% Dec: 100% |  | Thaworn/Chaicharn | Setup ESC system at ESC4 | Productivity | WIP
| AP | 2.3 | Study New Warehouse Management Platform for Specific Business : Cold Chain, Automotive, Retail | 92.31% Dec: 100% |  | Thaworn | Study New Warehouse Management Platform for Specific Business : Cold Chain, Automotive, Retail | Productivity | WIP
3. Create growth platform for regional integration | AP | 3.1 | Logistics system in South China | 92.31% Nov: 100% |  | Sarun/Sien | Logistics system in South China | Productivity | WIP | 4
4. Strengthen Infrastructure to Sustain Business | AP | 4.1.1 | Supply Chain Visibility: Delivery plan, SCV - Phase I (Internal SCG) | 85.71% Jun: 100% |  | Mongkolchai / Thaworn | Supply Chain Visibility: Delivery plan, SCV - Phase I (Internal SCG) | Delivery | Completed | 1
| AP | 4.1.2 | Logistics Command Center | 92.31% Jul: 100% |  | Mongkolchai/Eakapon | Logistics Command Center | Delivery | Completed | 2
| AP | 4.2 | Business Inteligence Phase I (Sales Report) | 92.31% Sep: 100% |  | Vatcham | Business Inteligence | Productivity | WIP
| AP | 4.3 | Proof of Delivery | 92.31% Dec: 100% |  | Mongkolchai | Proof of Delivery | Productivity | WIP
| Ad-hoc | 5 | SCTL link revamp | 92.31% Apr: 100% |  | Nattawut/Noppat
| Ad-hoc | 6 | SAP PI Implementation to replace P2P Integration with SAP R/3 | 92.31% Apr: 100% | Pending | Mongkolchai/Sarunya
| Ad-hoc | 7 | Document Management System: Roll-out | 100% Mar: 100% |  | Mongkolchai | Document Management System: Roll-out | Cost | Completed | 1
| Ad-hoc | 8 | System integration with Vitamilk | 85.71% Jun: 100% |  | Mongkolchai | System integration with Vitamilk | Productivity | Completed
| Ad-hoc | 9 | Pallet Management System | 92.31% Nov: 100% |  | Thaworn/Chaicharn | Pallet Management System | Productivity | WIP
| Ad-hoc | 10 | SAP New Pricing Structure | 92.31% Dec: 100% |  | Sarun/Sien | SAP New Pricing Structure | Productivity | WIP
| Ad-hoc | 11 | Supply Chain Visibility: Delivery plan, SCV - Phase II (For Customer) | 92.31% Nov: 100% |  | Mongkolchai / Thaworn | Supply Chain Visibility: Delivery plan, SCV - Phase II (For Customer) | Delivery | WIP | 1
| Ad-hoc | 12 | Truck inspection | 92.31% Nov: 100% |  | Sarunya/Sien | Truck inspection | Quality | WIP
| Ad-hoc | 13 | Kubota system Phase I | 100% Feb: 100% |  | Mongkolchai / Thaworn | Kubota system Phase I | Productivity | Completed
| Ad-hoc | 14 | Kubota system Phase II | 92.31% Jul: 100% |  | Mongkolchai / Thaworn | Kubota system Phase II | Productivity | Completed
| Ad-hoc | 15 | TROK web tracking | 75% Apr: 100%; 85.71% Jun: 100% |  | Isranu | TROK web tracking | Delivery | Completed
| Ad-hoc | 16 | TROK re-process | 92.31% Dec: 100% |  | Thaworn | TROK re-process | Productivity | WIP
| Ad-hoc | 17 | GPS Solution for Cold Chain Business | 92.31% Jul: 100% |  | Eakapon | GPS Solution for Cold Chain Business | Quality | Completed
| Ad-hoc | 18 | New billing | 92.31% Sep: 100% |  | Nattawuth / Sineekan | New billing | Quality | WIP
| Ad-hoc | 19 | TPC Interface@hub | 92.31% Jul: 100% |  | Sarunya | TPC Interface@hub | Delivery | Completed
| Ad-hoc | 20 | System integration with SCG Paper: SKIC Interface TMS Phase II | 92.31% Nov: 100% |  | Sarunya / Vatcharm | System integration with SCG Paper: SKIC Interface TMS Phase II | Productivity | WIP
| Ad-hoc | 21 | Claim & Complaint System | 75% Apr: 100% |  | Isranu | Claim & Complaint System | Quality | Completed | 1
10
[24 empty] | Tax relief | 2
Note on D4: Nattawuth Timrath: Original Plan from Annual Plan
Note on D5: Nattawuth Timrath: Add-hoc Project
Note on D6: Nattawuth Timrath: New Plan from Original Plan and Add-hoc project
Note on J6: Nattawuth Timrath: - TROK Web Tracking
Note on K6: Nattawuth Timrath: - System integration with SCG Paper: SKIC Interface TMS - Setup WMS and IT infrastructure at RDC Khonkaen
Note on O6: Nattawuth Timrath: Business Inteligence
Note on K17: Tanoos Pha-obsaeng (ธนุส ผะอบแสง): Delay caused from in-completed requirement - User / Customer
Note on K19: Tanoos Pha-obsaeng (ธนุส ผะอบแสง): Delay caused from construction - User
Note on J30: Tanoos Pha-obsaeng (ธนุส ผะอบแสง): Delay caused from customer readiness - Customer
Note on J37: Tanoos Pha-obsaeng (ธนุส ผะอบแสง): Delay caused from software incompatible - IT
Note on H43: Tanoos Pha-obsaeng (ธนุส ผะอบแสง): Delay caused from requirement changed - User

## Policy 2013 Old (hidden)
F-QMS-008
Action Plan : SCG Logistics Co.,Ltd. |  |  | Year 2013 |  |  | Dept. System Development Sect. - | [16 empty] | Date:_2/8/12_______________
No. | Company / Dept. Plan | Dept./ Sect. Plan | Control Point |  |  |  | Person | Due |  |  |  |  | Plan / Actual 2013 | [11 empty] | Plan / Actual 2014 |  |  |  | Evaluation
|  |  | Control item | Current | Target | +/- | in charge | Date |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Process | Results | Student
1 | Buildup capacity and improve service level for SCG | 1.1.1 System integration with SCG Paper: SKIC Interface TMS | Finish |  | 100% | - | Sarunya/Vatcharm | Feb-13 | Plan |  |  | 30% | 70% | 100%
[9 empty] | Actual |  |  | 30% | 50% | 50% | 60% | 65% | 70%
|  |  | Reduce AR/AP Period | 30 days | 21 days |  |  |  | Plan | [5 empty] | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
[9 empty] | Actual | [5 empty] | - | - | -
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Dec-12 | Plan |  |  | 30%
[9 empty] | Actual |  |  | 30%
|  | - UAT | Finish |  | 70% |  |  | Jan-13 | Plan |  |  |  | 70%
[9 empty] | Actual |  |  |  | 50% | 50% | 60% | 65% | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Feb-13 | Plan |  |  |  |  | 100% |  |  |  | 90% | 100%
[8 empty] | 2013-07-01 | Actual | [8 empty] | 80%
|  | 1.1.2 System integration with SCG Paper: Interface TCG System to TMS | Finish |  | 100% | - | Sarunya | Jan-14 | Plan | [9 empty] | 30% |  |  |  | 70% |  | 100%
Actual
|  |  | Reduce AR/AP Period | 30 days | 21 days |  |  |  | Plan | [16 empty] | 21 | 21 | 21
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Jul-13 | Plan | [9 empty] | 30%
Actual
|  | - UAT | Finish |  | 70% |  |  | Nov-13 | Plan | [13 empty] | 70%
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jan-14 | Plan | [15 empty] | 100%
Actual
2 | Warehouse expansion for customer response | 2.1 Setup WMS and IT infrastructure at RDC Khonkaen | Finish |  | 100% | - | Nattawut / Thaworn | Mar-13 | Plan |  | 30$ |  |  | 70% | 100%
| and efficiency improvement | [7 empty] | Actual |  | 20% | 30% | 30% | 30% | 30% | 40% | 60% | 65%
|  |  | Data accuracy | N/A | 100% |  |  |  | Plan | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[9 empty] | Actual | [6 empty] | - | -
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Nov-12 | Plan |  | 30%
[9 empty] | Actual |  | 20% | 30%
|  | - UAT | Finish |  | 70% |  |  | Feb-13 | Plan |  |  |  |  | 70%
[9 empty] | Actual |  |  |  | 30% | 30% | 30% | 40% | 60% | 65%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Mar-13 | Plan | [5 empty] | 100%
Actual
|  | 2.2 Setup ESC system at ESC4 | Finish |  | 100% | - | Thaworn/Chaicharn |  | Plan | [14 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan | [14 empty] | 100%
Actual
|  | 2.3 Study New Warehouse Management Platform for Specific Business : Cold Chain, Automotive, Retail | Finish |  | 100% | - | Thaworn |  | Plan | [14 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  |  | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  |  | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  |  | Plan | [14 empty] | 100%
Actual
3 | Create growth platform for regional integration | 3.1 Logistics system in South China | Finish |  | 100% |  | Sarun/Sien |  | Plan | [9 empty] | 30% |  |  | 70% | 100%
[9 empty] | Actual | [7 empty] | 15%
|  |  | Data reliability | xx | 100% |  |  |  | Plan
Actual
|  |  | Reduce post GR process | 24 Hours | 0 Hour |  |  |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Jul-13 | Plan | [9 empty] | 30%
[9 empty] | Actual | [7 empty] | 15%
|  | - UAT | Finish |  | 70% |  |  | Oct-13 | Plan | [12 empty] | 70%
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Nov-13 | Plan | [13 empty] | 100%
Actual
4 | Strengthen infrastructure to sustain business | 4.1.1 Logistics Command Center | Finish |  | 100% | - | Mongkolchai/Eakapon |  | Plan | [6 empty] | 30% |  | 70% | 100%
[9 empty] | Actual | [6 empty] | 30% |  | 100%
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Apr-13 | Plan | [6 empty] | 30%
[9 empty] | Actual | [6 empty] | 30%
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan | [8 empty] | 70%
[9 empty] | Actual | [7 empty] | 50% | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jul-13 | Plan | [9 empty] | 100%
[9 empty] | Actual | [8 empty] | 100%
|  | 4.1.2 Supply Chain Visibility: Delivery plan, SCV - Phase I (Internal SCG) | Finish |  | 100% | - | Mongkolchai / Thaworn |  | Plan | [7 empty] | 30% | 100%
[9 empty] | Actual | [7 empty] | 30% | 100%
|  |  | Reduce time usage to check truck status | 60 Mins. | 10 Mins. |  |  |  | Plan | [9 empty] | 10 | 10 | 10 | 10 | 10 | 10
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan | [7 empty] | 30%
[9 empty] | Actual | [7 empty] | 30%
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan | [8 empty] | 70%
[9 empty] | Actual | [8 empty] | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [8 empty] | 100%
[9 empty] | Actual | [8 empty] | 100%
|  | 4.2 Business Intelligence | Finish |  | 100% | - | Vatcham |  | Plan | [14 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [14 empty] | 100%
Actual
|  | 4.3 Proof of Delivery | Finish |  | 100% | - | Mongkolchai |  | Plan | [14 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [14 empty] | 100%
Actual
|  | 5. SCTL link revamp | Finish |  | 100% | - | Nattawut/Noppat | Apr-14 | Plan | [11 empty] | 15% | 30% |  |  |  | 70% |  | 100%
[9 empty] | Actual |  |  |  | 1% | 2% | 3% | 4% | 5% | 6%
|  |  | Reduce redundant data entry | x1 | y1 |  |  |  | Plan
Actual
|  |  | Reduce AP/AR period | x2 | y2 |  |  |  | Plan
Actual
|  |  | Reduce admin cost / Trans | x3 | y3 |  |  |  | Plan
Actual
|  | - Confirm Business Requirement / New solution design / |  |  | 15% |  |  | Sep-13 | Plan | [11 empty] | 15%
|  | Vendor Selection and Budget Approval | [6 empty] | Actual |  |  |  | 1% | 2% | 3% | 4% | 5% | 6%
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Oct-13 | Plan | [12 empty] | 30%
Actual
|  | - UAT | Finish |  | 70% |  |  | Feb-14 | Plan | [16 empty] | 70%
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Apr-14 | Plan | [18 empty] | 100%
Actual
|  | 6. SAP PI Implementation to replace P2P Integration with SAP R/3 | Finish |  | 100% | - | Mongkolchai/Sarunya |  | Plan
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan
Actual
|  | 7. Document Management System: Roll-out | Finish |  | 100% | - | Mongkolchai |  | Plan |  |  |  |  | 30% | 100%
[9 empty] | Actual |  |  |  |  | 30% | 100%
|  |  | Data Accuracy | 70% | 100% |  |  |  | Plan | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[9 empty] | Actual | [5 empty] | 80% | 100% | 100% | 100%
|  |  | Time usage to upload | 2 Hours | 0,5 Hours |  |  |  | Plan | [6 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[9 empty] | Actual | [6 empty] | 0.5 | 0.5
|  |  | จำนวนลูกค้าที่ใช้งานระบบ | 73 | 216 |  |  |  | Plan | [5 empty] | 216
[9 empty] | Actual |  |  |  | 73 | 156 | 216
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Feb-13 | Plan |  |  |  |  | 30%
[9 empty] | Actual |  |  |  |  | 30%
|  | - UAT | Finish |  | 70% |  |  | Mar-13 | Plan | [5 empty] | 70%
[9 empty] | Actual | [5 empty] | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Mar-13 | Plan | [5 empty] | 100%
[9 empty] | Actual | [5 empty] | 100%
|  | - Roll-out | จำนวนลูกค้า | 216 | 438 |  |  | Jun-13 | Plan | [6 empty] | 300 | 400 | 438
[9 empty] | Actual | [6 empty] | 216 | 216 | 216
|  |  | จำนวนหน่วยงาน | 3 | 16 |  |  | Jul-13 | Plan | [7 empty] | 4 | 12 | 16
[9 empty] | Actual | [7 empty] | 3 | 3
|  | 8. System integration with Vitamilk | Finish |  | 100% | - | Mongkolchai |  | Plan | [5 empty] | 30% | 70% | 100% | 100%
[9 empty] | Actual | [5 empty] | 30% | 60% | 80% | 95%
|  |  | Reduce Shipment Planning Time | 4 Hours / day | 2 Hours / day |  |  |  | Plan | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[9 empty] | Actual | [7 empty] | 4 | 4
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Mar-13 | Plan | [5 empty] | 30%
[9 empty] | Actual | [5 empty] | 30%
|  | - UAT | Finish |  | 70% |  |  | Arp-13 | Plan | [6 empty] | 70%
[9 empty] | Actual | [6 empty] | 60% | 70%
|  | - Go-live & Post Support | Finish |  | 100% |  |  | May-13 | Plan | [7 empty] | 100% | 100%
[9 empty] | Actual | [7 empty] | 80% | 95%
|  | 9. Pallet Management System | Finish |  | 100% | - | Thaworn/Chaicharn |  | Plan | [9 empty] | 30% |  |  | 70% | 100%
Actual
|  |  | Data accuracy | N/A | 99% |  |  |  | Plan | [14 empty] | 99%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Jul-13 | Plan | [9 empty] | 30%
Actual
|  | - UAT | Finish |  | 70% |  |  | Oct-13 | Plan | [12 empty] | 70%
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Nov-13 | Plan | [13 empty] | 100%
Actual
|  | 10. SAP New Pricing Structure | Finish |  | 100% | - | Sarun/Sien |  | Plan | [9 empty] | 30% |  |  | 70% |  | 100%
[9 empty] | Actual | [7 empty] | 10% | 15%
|  |  | Reduce time usage to maintain price per month | xx Hour | 0 Hour |  |  |  | Plan | [15 empty] | 0 | 0 | 0 | 0
Actual
|  |  | Data accuracy (Billing) | xxx | 100% |  |  |  | Plan | [15 empty] | 100% | 100% | 100% | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Jul-13 | Plan | [9 empty] | 30%
[9 empty] | Actual | [7 empty] | 10% | 15%
|  | - UAT | Finish |  | 70% |  |  | Oct-13 | Plan | [12 empty] | 70%
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Dec-13 | Plan | [14 empty] | 100%
Actual
|  | 11. Supply Chain Visibility: Delivery plan, SCV - Phase II (For Customer) | Finish |  | 100% | - | Mongkolchai / Thaworn |  | Plan | [10 empty] | 30% |  | 70% | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | Aug-13 | Plan | [10 empty] | 30%
Actual
|  | - UAT | Finish |  | 70% |  |  | Oct-13 | Plan | [12 empty] | 70%
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Nov-13 | Plan | [13 empty] | 100%
Actual
|  | 12. Truck inspection | Finish |  | 100% | - | Sarunya/Sien |  | Plan | [13 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [13 empty] | 100%
Actual
|  | 13. Kubota system Phase I | Finish |  | 100% | - | Mongkolchai / Thaworn |  | Plan |  |  |  |  | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan |  |  |  |  | 100%
Actual
|  | 14. Kubota system Phase II | Finish |  | 100% | - | Mongkolchai / Thaworn |  | Plan | [9 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [9 empty] | 100%
Actual
|  | 15. TROK web tracking | Finish |  | 100% | - | Isranu |  | Plan | [6 empty] | 100% |  | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [6 empty] | 100% |  | 100%
Actual
|  | 16. TROK re-process | Finish |  | 100% | - | Thaworn |  | Plan | [12 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [12 empty] | 100%
Actual
|  | 17. GPS Solution for Cold Chain Business | Finish |  | 100% | - | Eakapon |  | Plan | [9 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [9 empty] | 100%
Actual
|  | 18. New Billing | Finish |  | 100% | - | Nattawuth / Sineekan |  | Plan | [11 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [11 empty] | 100%
Actual
|  | 19. TPC Interface@hub | Finish |  | 100% | - | Sarunya |  | Plan | [9 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [9 empty] | 100%
Actual
|  | 20. System integration with SCG Paper: SKIC Interface TMS Phase II | Finish |  | 100% | - | Sarunya / Vatcharm |  | Plan | [13 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [13 empty] | 100%
Actual
|  | 21. Claim & Complaint System | Finish |  | 100% | - | Isranu |  | Plan | [6 empty] | 100%
Actual
|  | - Confirm Detail requirement (DRS) | Finish |  | 30% |  |  | May-13 | Plan
Actual
|  | - UAT | Finish |  | 70% |  |  | Jun-13 | Plan
Actual
|  | - Go-live & Post Support | Finish |  | 100% |  |  | Jun-13 | Plan | [6 empty] | 100%
Actual
Approve by _____________________ Date _______________________
F-QMS-008 (REV.3)
Plan
Actual
Plan
Actual
Note on E7: Nattawuth Timrath: งานเข้าระบบ - รับรู้รายได้ทันที (เดิมเป็น Monthly เป็น Daily) - การติดตาม overdue เดิม Monthly เป็น Daily) - เวลาในการสรุป Billing เก็บ-จ่าย (ควร) ต้องลดลง - ความน่าเชื่อถือของข้อมูล
Note on T13: Training - completed Maintain AR/AP - In-progress
Note on J14: Revise
Note on T14: maintain 1. ค่าเก็บลูกค้า - ม้วน-> พี่จูบ maintain แล้วเสร็จ, พี่อี๊ดเอาเข้าระบบ - เศษโรงอัด ราคา Backhaul (อยุธยา, ขอนแก่น) -> พี่อี๊ด maintain เพิ่ม โดยใช้ Template เดิม 2. ค่าจ่าย ผรม. - ม้วน -> พี่ก้อง maintain แล้วเสร็จ อยู่ระหว่างตรวจสอบความถูกต้อง - เศษโรงอัด ราคา Backhaul (อยุธยา, ขอนแก่น) -> พี่อี๊ด ส่งราคาให้พี่ X
Note on E27: Nattawuth Timrath: %Stock Acc. %Inventory Acc. %Picking Acc. %Putaway Acc. %Recieved Acc.
Note on E73: Nattawuth Timrath: ลดเวลาในการสอบถามสถานะการขนส่งเพื่อตอบลูกค้า
Note on E123: Nattawuth Timrath: Data accuracy หมายถึง สามารถ upload DN ได้ถูกต้อง

## Project achievement rate
Good

## %Raito Project Success
| 2010 | 2011 | 2012 | H1/2013 | 2013
Action Plan | 5 | 4 | 7 | 4 | 11
Ad Hoc | 9 | 12 | 12 | 8 | 15
TOTAL | 14 | 16 | 19 | 12 | 26
Success | 11 | 14 | 15 | 12 | 0
Failed | 1 | 0 | 0 | 2 | 0
Impact to Customer | 2 | 2 | 4 | 4 | 4
% Ratio Project Success | 91.67% | 100% | 100% | 85.71% | #DIV/0!
| 2010 | 2011 | 2012 | 2013-07-01 | 2013
Success | 11 | 14 | 15 | 12 | 15
Failed | 1 | 0 | 0 | 1 | 0
% Ratio Project Success | 91.67% | 100% | 100% | 92.31% | 100%
% Plan project success | 90% | 90% | 90% | 90% | 90%
Note on A6: Nattawuth Timrath: Project ที่ไม่สำเร็จเนื่องจากปัญหาของเราเอง
Note on A7: Nattawuth Timrath: Project ที่ไม่ success ที่เป็นปัจจัยที่ควบคุมไม่ได้ เช่น ลูกค้า
Note on A12: Nattawuth Timrath: Project ที่ไม่สำเร็จเนื่องจากปัญหาของเราเอง
Good

## Sheet5
Count of IT Plan
Type | Total
Cost | 1
Delivery | 5
Productivity | 14
Quality | 4
Grand Total | 24

## Sheet6
Count of IT Plan | Status
Type | Completed | WIP | Grand Total
Productivity | 4 | 10 | 14
Cost | 1 |  | 1
Quality | 2 | 2 | 4
Delivery | 4 | 1 | 5
Grand Total | 11 | 13 | 24

## Sheet2
Count of Type | Status
Type | Completed | WIP | Grand Total
Cost | 1 |  | 1
Delivery | 3 | 2 | 5
Productivity | 4 | 9 | 13
Quality | 3 | 2 | 5
Grand Total | 11 | 13 | 24

## Sheet1
IT Project |  | Implementation Effort | Impact to Business
System integration with SCG Paper: SKIC Interface TMS | Action Plan
System integration with SCG Paper: Interface TCG System to TMS | Action Plan
SCTL link revamp | Action Plan
Setup WMS and IT infrastructure at RDC Khonkaen | Action Plan
Setup ESC system at ESC4 | Action Plan
Study New Warehouse Management Platform for Specific Business : Cold Chain, Automotive, Retail | Action Plan
Logistics system in South China | Action Plan
Logistics Command Center | Action Plan
SAP PI Implementation to replace P2P Integration with SAP R/3 | Action Plan
Business Inteligence | Action Plan
Proof of Delivery | Action Plan
Document Management System: Roll-out | Ad-hoc
System integration with Vitamilk | Ad-hoc
Pallet Management System | Ad-hoc
SAP New Pricing Structure | Ad-hoc
Supply Chain Visibility: Delivery plan, SCV - Phase I (Internal SCG) | Ad-hoc
Supply Chain Visibility: Delivery plan, SCV - Phase II (For Customer) | Ad-hoc
Truck inspection | Ad-hoc
Kubota system Phase I | Ad-hoc
Kubota system Phase II | Ad-hoc
TROK web tracking | Ad-hoc
TROK re-process | Ad-hoc
GPS Solution for Cold Chain Business | Ad-hoc
New billing | Ad-hoc
TPC Interface@hub | Ad-hoc
System integration with SCG Paper: SKIC Interface TMS Phase II | Ad-hoc